## Change Log
Change ID | Change | Reason | Impact | Date
C01 | Removed CONSTRAINT from duplicate foreign keys | Fixes error found in test case S01_C07 & S01_C08 | Tables with shared foreign keys can be created without error | 2025-03-31
C02 | Added section comments | Organisation | Better visual clarity | 2025-03-31
C03 | Replaced getdate() with now(), dateadd() with date_add(), and fixed typo in PurchaseUniform | GETDATE() and DATEADD() are valid in SQL Server, but not for MySQL as learnt from P03 | Allows PurchaseUniform procedure to work | 2025-04-01
C04 | Made role_id = roleInput in AddNewStaff procedures select line instead of 1 | Forget to do after testing during development with hard coded responces | AddNewStaff returns uniform for specified role instead of always the Doctors | 2025-04-01
C05 | Flipped bool requirement value in PurchaseUniform's IF statement | Bool value incorrectly assigned in IF statement as found in P06 | Purchased uniforms no longer have a reissue date, and vice versa | 2025-04-01
C06 | Added range check to tables | Input validation | Prevents negative and zero values where there shouldn't | 2025-04-02
C07 | Replaced tbl_orders bought columns bool with bit(1) | BOOL is just TINYINT(1) aliased, which is the cause of the lack of range validation | Range is now limited to 1 or 0 | 2025-04-02
C08 | Changed database name for easier readability | Better readability | Better readability | 2025-04-02
C09 | Changed connection to databade to connection pooling | Database is going to be accessed multiple times, this should help performance | Better resource and hopefully time management | 2025-04-02
C10 | Imported specific functions instead to simplify code | Makes my life easier when coding future functions | Better readability and management of code | 2025-04-03
C11 | Added labels to PurchaseUniform()'s SELECT statement | front end pulls the column names directly from the database | Better visuals in GUI | 2025-04-03
C12 | Removed item_name from AddNewStaff()'s SELECT statement | Redundant as I don't think I'll display the created order in the GUI anymore | Should help with fetch time | 2025-04-03
C13 | Removed plurality from role names | Tends to read better in cases where displayed | Better punctuality | 2025-04-05
C14 | Split AddNewStaff into two | Allows me to use the more complicated select query while also preventing a double entry bug discovered | Better code reusablility and prevents duplicate entry bug | 2025-04-08
C15 | Expanded PurchaseUniform to remove reissue date from reissued uniforms | Allows me to just use PurchaseUniform without an extra query or procedure | Code reusability | 2025-04-09
C16 | Capitalised colour names | These strings are used in GUI display | Better visuals in GUI | 2025-04-09
C17 | Expanded AvailableReissues select statement | Displays better values instead of id's and new columns | Better data reponsenation and values | 2025-04-10
C18 | PurchaseUniform now sets reissued orders reissue date to none | Prevents orders being reissued twice or for a second procedure to be called to do it | Improved function and reduced need for additional calls | 2025-04-10
C19 | Combined AddNewStaff and LastAddedStaff | LastAddedStaff is always called after AddNewStaff, so makes sense to combine then | Reduces number of database calls | 2025-04-11
C20 | Added CONCAT to AvailableReissues | Combines two columns into one for better reponsentation | Better visuals in GUI | 2025-04-11
C21 | Added left join to AvailableReissues | Rows where being not returned due to colout value being null | Returns results accurately | 2025-04-11
C22 | Added colour_id to select in AvailableReissues | Can no longer get the colour due to it beign concat'd with uniform and string splicing will have issues when colour is null | Better functionality | 2025-04-11
C23 | Added back accidently removed FindStaff() procedure | Mistaken as redundant when needed as part of the staff search function by role | Makes staff search class fucntional again | 2025-04-11
C24 | Fixed incorrect usage of StaffSearch class in staff and order modules | Wasn't quite getting the right values for procedure args | Less errors when using StaffSearch class | 2025-04-11
C25 | Reissue orders now auto refresh table | Forgotten and should have been in already | Better user experience | 2025-04-11
C26 | Added null validation to StaffSelection class | even in try except blocks, missing values cause issues | Reduces chance of crashes or errors | 2025-04-12
C27 | Added null validation to 'Staff Details' menu | even in try except blocks, missing values cause issues | Reduces chance of crashes or errors | 2025-04-12
C28 | Added null validation to 'Uniform Selection' menu | even in try except blocks, missing values cause issues | Reduces chance of crashes or errors | 2025-04-12
| *Only post test changes documented, see GitHub blame for all changes and additions | https://github.com/JamesBullen/Uniform-Distribution-System

## Requirements
Req. ID | Req. Description
R_01 | Staff are issued uniforms when joining the service.
R_02 | Full-time staff receive the uniform allocation as set out in the Uniform Allocation Criteria table. Parttime staff will receive a proportional allocation according to the number of base hours worked.
R_03 | The uniform entitlement should be drawn from the Uniform Allocation Criteria table using the Working role data.
R_04 | On the Uniform Issue Record, the reissue date should be automatically calculated based on Date of issue + 24 months.
R_05 | On the Uniform Issue Record, staff have the option to purchase additional items of uniform. If they are making an additional purchase, this should be identified, and staff will need to pay before the issue takes place. These should not be reissued in the normal way

## Schema Testing
Scenario ID | Scenario Description | Case ID | Req. ID | Case Description | Query | Date | Status | Expected Results | Actual Results | Comments
S01 | Check if tables created | S01_C01 |  | Check roles table | select * from tbl_roles; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S01_C02 |  | Check colours table | select * from tbl_colours; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S01_C03 |  | Check sizes table | select * from tbl_sizes; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S01_C04 |  | Check suppliers table | select * from tbl_suppliers; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S01_C05 |  | Check uniforms table | select * from tbl_uniforms; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S01_C06 |  | Check allocations table | select * from tbl_allocations; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S01_C07 |  | Check staff table | select * from tbl_staff; | 2025-03-31 | FAIL | Empty table displayed | Error 1146, table doesn't exist | Error 1826 prevented creation
|  | S01_C08 |  | Check orders table | select * from tbl_orders; | 2025-03-31 | FAIL | Empty table displayed | Error 1146, table doesn't exist | Error 1826 prevented creation
S02 | Check if data inserted correctly | S02_C01 |  | Check roles table | select * from tbl_roles; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S02_C02 |  | Check colours table | select * from tbl_colours; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S02_C03 |  | Check sizes table | select * from tbl_sizes; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S02_C04 |  | Check suppliers table | select * from tbl_suppliers; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S02_C05 |  | Check uniforms table | select * from tbl_uniforms; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S02_C06 |  | Check allocations table | select * from tbl_allocations; | 2025-03-31 | PASS | Show table with correct data | As expected
S03 | Check if tables created after fix C01 | S03_C01 |  | Check roles table | select * from tbl_roles; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S03_C02 |  | Check colours table | select * from tbl_colours; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S03_C03 |  | Check sizes table | select * from tbl_sizes; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S03_C04 |  | Check suppliers table | select * from tbl_suppliers; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S03_C05 |  | Check uniforms table | select * from tbl_uniforms; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S03_C06 |  | Check allocations table | select * from tbl_allocations; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S03_C07 |  | Check staff table | select * from tbl_staff; | 2025-03-31 | PASS | Empty table displayed | As expected
|  | S03_C08 |  | Check orders table | select * from tbl_orders; | 2025-03-31 | PASS | Empty table displayed | As expected
S04 | Check if data inserted correctly after fix C01, regression test | S04_C01 |  | Check roles table | select * from tbl_roles; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S04_C02 |  | Check colours table | select * from tbl_colours; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S04_C03 |  | Check sizes table | select * from tbl_sizes; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S04_C04 |  | Check suppliers table | select * from tbl_suppliers; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S04_C05 |  | Check uniforms table | select * from tbl_uniforms; | 2025-03-31 | PASS | Show table with correct data | As expected
|  | S04_C06 |  | Check allocations table | select * from tbl_allocations; | 2025-03-31 | PASS | Show table with correct data | As expected
S05 | Check if tables created redundancy test | S05_C01 |  | Check roles table | select * from tbl_roles; | 2025-04-11 | PASS | Empty table displayed | As expected
|  | S05_C02 |  | Check colours table | select * from tbl_colours; | 2025-04-11 | PASS | Empty table displayed | As expected
|  | S05_C03 |  | Check sizes table | select * from tbl_sizes; | 2025-04-11 | PASS | Empty table displayed | As expected
|  | S05_C04 |  | Check suppliers table | select * from tbl_suppliers; | 2025-04-11 | PASS | Empty table displayed | As expected
|  | S05_C05 |  | Check uniforms table | select * from tbl_uniforms; | 2025-04-11 | PASS | Empty table displayed | As expected
|  | S05_C06 |  | Check allocations table | select * from tbl_allocations; | 2025-04-11 | PASS | Empty table displayed | As expected
|  | S05_C07 |  | Check staff table | select * from tbl_staff; | 2025-04-11 | PASS | Empty table displayed | As expected
|  | S05_C08 |  | Check orders table | select * from tbl_orders; | 2025-04-11 | PASS | Empty table displayed | As expected
S06 | Check if data inserted correctly redundancy | S06_C01 |  | Check roles table | select * from tbl_roles; | 2025-04-11 | PASS | Show table with correct data | As expected
|  | S06_C02 |  | Check colours table | select * from tbl_colours; | 2025-04-11 | PASS | Show table with correct data | As expected
|  | S06_C03 |  | Check sizes table | select * from tbl_sizes; | 2025-04-11 | PASS | Show table with correct data | As expected
|  | S06_C04 |  | Check suppliers table | select * from tbl_suppliers; | 2025-04-11 | PASS | Show table with correct data | As expected
|  | S06_C05 |  | Check uniforms table | select * from tbl_uniforms; | 2025-04-11 | PASS | Show table with correct data | As expected
|  | S06_C06 |  | Check allocations table | select * from tbl_allocations; | 2025-04-11 | PASS | Show table with correct data | As expected

## Procedure Testing
Scenario ID | Scenario Description | Case ID | Req. ID | Case Description | Query | Pre-Conditions | Date | Status | Expected Results | Actual Results | Comments
P01 | Check AddNewStaff | P01_C01 | R_01, R_03 | Check if returns data needed for a uniform order | call AddNewStaff('James Bullen', 'M', 1, 40); | tbl_staff dropped and recreated | 2025-04-01 | PASS | Table with allocated item name, item ID, colour id, sizes ID, quantity | As expected | Clearing a table does not reset its auto increment counter. Must be dropped and created again
|  | P01_C02 | R_02 | Check if quantity changes based on hours | call AddNewStaff('Matilda Carboni', 'F', 6, 8); | tbl_staff dropped and recreated | 2025-04-01 | FAIL | Table with allocated item name, item ID, colour id, sizes ID, quantity | Returned wrong colour ID
P02 | Check LastAddedStaff | P02_C01 |  | Check if returns ID of last added staff | call LastAddedStaff(); |  | 2025-04-01 | PASS | Return ID for staff added in P01_C02 | As expected
P03 | Check PurchaseUniform | P03_C01 | R_04 | Check if returns data with current date and reissue date | call PurchaseUniform(1, 1, 1, null, 'XS', 3, 0); select * from tbl_orders where order_id = (select max(order_id) from tbl_orders); | tbl_orders dropped and recreated. P01 ran | 2025-04-01 | FAIL | Single row with details from P01_C01 and dates | Error 1054, unknown column itemID | Typo where itemID was wrote instead of itemInput in the procedure
|  | P03_C02 | R_05 | Check if no reissue date if bought | call PurchaseUniform(2, 1, 1, null, 'XS', 3, 1); select * from tbl_orders where order_id = (select max(order_id) from tbl_orders); | tbl_orders dropped and recreated. P01 ran | 2025-04-01 | FAIL | Single row with details from P01_C02 and no reissue date | Error 1054, unknown column itemID
P04 | Check AddNewStaff after fix C04 | P04_C01 | R_01, R_03 | Check if returns data needed for a uniform order | call AddNewStaff('James Bullen', 'M', 1, 40); | tbl_staff dropped and recreated | 2025-04-01 | PASS | Table with allocated item name, item ID, colour id, sizes ID, quantity | As expected
|  | P04_C02 | R_02 | Check if quantity changes based on hours | call AddNewStaff('Matilda Carboni', 'F', 6, 8); | tbl_staff dropped and recreated | 2025-04-01 | PASS | Table with allocated item name, item ID, colour id, sizes ID, quantity | As expected
P05 | Regression check LastAddedStaff | P05_C01 |  | Check if returns ID of last added staff | call LastAddedStaff(); |  | 2025-04-01 | PASS | Return ID for staff added in P01_C02 | As expected
P06 | Check PurchaseUniform after fix C03 | P06_C01 | R_04 | Check if returns data with current date and reissue date | call PurchaseUniform(1, 1, 1, null, 'XS', 3, 0); select * from tbl_orders where order_id = (select max(order_id) from tbl_orders); | tbl_orders dropped and recreated. P01 ran | 2025-04-01 | FAIL | Single row with details from P06_C01 and dates | No reissue date
|  | P06_C02 | R_05 | Check if no reissue date if bought | call PurchaseUniform(2, 1, 1, null, 'XS', 3, 1); select * from tbl_orders where order_id = (select max(order_id) from tbl_orders); | tbl_orders dropped and recreated. P01 ran | 2025-04-01 | FAIL | Single row with details from P06_C02 and no reissue date | Reissue date where there shouldn't be | Boolean just needs to be flipped for correct results along with P06_C01
P07 | Check PurchaseUniform after fix C05 | P07_C01 | R_04 | Check if returns data with current date and reissue date | call PurchaseUniform(1, 1, 1, null, 'XS', 3, 0); select * from tbl_orders where order_id = (select max(order_id) from tbl_orders); | tbl_orders dropped and recreated. P01 ran | 2025-04-01 | PASS | Single row with details from P01_C01 and dates | As expected
|  | P07_C02 | R_05 | Check if no reissue date if bought | call PurchaseUniform(2, 1, 1, null, 'XS', 3, 1); select * from tbl_orders where order_id = (select max(order_id) from tbl_orders); | tbl_orders dropped and recreated. P01 ran | 2025-04-01 | PASS | Single row with details from P01_C01 and no reissue date | As expected
P08 | Check AvailableReissues | P08_C01 | R_04 | Check with no orders | call AvailableReissues() | Truncate tbl_orders | 2025-04-02 | PASS | Show no orders | As expected
|  | P08_C02 | R_04 | Check with all orders having valid reissue dates | call AvailableReissues() | Add order with past reissue dates | 2025-04-02 | FAIL | Show all added orders | Missing entries | Items with null for their colour results in the whole row disapearing
|  | P08_C03 | R_04 | Check with half orders having valid reissue dates | call AvailableReissues() | Add order with future reissue dates | 2025-04-02 | FAIL | Show half the orders | Missing entries
P09 | Check AddStaff after change C19 | P09_C01 | R_01, R_03 | Check if returns data needed for a uniform order | call AddNewStaff('James Bullen', 'M', 1, 40); | tbl_staff dropped and recreated | 2025-04-11 | PASS | Accepted call, update tbl_staff, return ID | As expected | Has been slightly renamed, same as AddNewStaff()
|  | P09_C02 |  | Check if returns correct id of the added staff | call AddNewStaff('Matilda Carboni', 'F', 6, 8); | tbl_staff dropped and recreated | 2025-04-11 | PASS | Return an ID of 2 | As expected
P10 | Check PurchaseUniform after changes C15 and C18 | P10_C01 | R_04 |  | call PurchaseUniform(1, 1, 1, null, 'XS', 3, 0, 0); select * from tbl_orders where order_id = (select max(order_id) from tbl_orders); | tbl_orders dropped and recreated and P09 ran | 2025-04-11 | PASS | Single row with details from P10_C01 and dates | As expected
|  | P10_C02 | R_05 | Check if no reissue date if bought | call PurchaseUniform(2, 1, 1, null, 'XS', 3, 1, 0); select * from tbl_orders where order_id = (select max(order_id) from tbl_orders); | tbl_orders dropped and recreated and P09 ran | 2025-04-11 | PASS | Single row with details from P10_C02 and no reissue date | As expected
|  | P10_C03 | R_04 | Check if order 1's reissue date is removed | call PurchaseUniform(3, 1, 1, null, 'XS', 3, 0, 1); select * from tbl_orders; | Previous P10 cases ran | 2025-04-11 | PASS | Single row with details from P10_C03 and reissue date change for order 1 | As expected
P11 | Check AvailableReissues after change C17 and C20 | P11_C01 | R_04 | Check with no orders | call AvailableReissues() | Truncate tbl_orders | 2025-04-11 | PASS | Return no rows | As expected
|  | P11_C02 | R_04 | Check with all orders having valid reissue dates | call AvailableReissues() | Add order with past reissue dates | 2025-04-11 | PASS | Return one row | As expected
|  | P11_C03 | R_04 | Check with half orders having valid reissue dates | call AvailableReissues() | Add order with future reissue dates | 2025-04-11 | PASS | Return one row | As expected
P12 | Check RetireStaff | P12_C01 |  | Check if staff is removed | call RetireStaff(2); select * from tbl_staff; |  | 2025-04-11 | PASS | Staffer 2 removed | As expected
P13 | Check AllocationUniform | P13_C01 |  | Check male doctor with 40 hours | call AllocatedUniform('M', 1, 40); |  | 2025-04-11 | PASS | 4 rows, male uniform, max quantity | As expected
|  | P13_C02 |  | Check female doctor with 40 hours | call AllocatedUniform('F', 1, 40); |  | 2025-04-11 | PASS | 4 rows, female uniform, max quantity | As expected
|  | P13_C03 |  | Check male nurse with 40 hours | call AllocatedUniform('M', 2, 40); |  | 2025-04-11 | PASS | 3 rows, male uniform, max quantity | As expected
|  | P13_C04 |  | Check male nurse with 8 hours | call AllocatedUniform('M', 2, 8); |  | 2025-04-11 | PASS | 3 rows, male uniform, 1 of each | As expected
P14 | Check NextOrderNumber | P14_C01 |  | Check if returns highest order number plus one | call nextOrderNumber(); |  | 2025-04-11 | PASS | Returns 2 | As expected
P15 | Check StaffInfo | P15_C01 |  | Check if returns all staff | call StaffInfo(1); | Add back removed staff | 2025-04-11 | PASS | Returns all staff | As expected
|  | P15_C02 |  | Check if returns select amount of recent staff | call StaffInfo(2); |  | 2025-04-11 | PASS | Returns just one | As expected
P16 | Check OrderInfo | P16_C01 |  | Check if returns all orders | call OrderInfo(1); |  | 2025-04-11 | PASS | Returns all orders | As expected
|  | P16_C02 |  | Check if returns select amount of recent orders | call OrderInfo(2); |  | 2025-04-11 | PASS | Returns just one | As expected
P17 | Check MostOrdered | P17_C01 |  | Check if returns uniform grouped by quantity ordered | call MostOrdered(); |  | 2025-04-11 | PASS |  | As expected
P18 | Check StaffStatistics | P18_C01 |  |  | call StaffStatistics(); |  | 2025-04-11 | PASS |  | As expected
P19 | Check AllocationTable | P19_C01 |  | Check if it returns all uniform | call AllocationTable(); |  | 2025-04-11 | PASS | Table with all uniform ordered by role | As expected
P20 | Check AvailableReissues after change C21 and C22 | P11_C01 | R_04 | Check with no orders | call AvailableReissues() | Truncate tbl_orders | 2025-04-11 | PASS | Return no rows | As expected
|  | P11_C02 | R_04 | Check with all orders having valid reissue dates | call AvailableReissues() | Add order with past reissue dates | 2025-04-11 | PASS | Return one row | As expected
|  | P11_C03 | R_04 | Check with half orders having valid reissue dates | call AvailableReissues() | Add order with future reissue dates | 2025-04-11 | PASS | Return one row | As expected
P21 | Check FindStaff | P21_C01 |  | Check if returns all doctors | call FindStaff(1); |  | 2025-04-11 | PASS | Return doctor | As expected
|  | P21_C02 |  | Check if returns all nurses | call FindStaff(2); | Add nurse staff | 2025-04-11 | PASS | Return nurse | As expected
|  | P21_C03 |  | Check if returns all HCA | call FindStaff(3); |  | 2025-04-11 | PASS | No rows | As expected

## Mapping Testing
Scenario ID | Scenario Description | Case ID | Req. ID | Case Description | Steps | Pre-Conditions | Date | Status | Expected Results | Actual Results | Comments
M01 | Add new staff to system | M01_C01 |  | Check if new staff can be added | Click on 'Add Staffer' Fill out staff info Click 'Next' Select uniform sizes Click 'Finish' |  | 2025-04-11 | PASS | Staff entered into database | As expected
|  | M01_C02 |  | Check if can go back to staff details with values present from uniform selection | Click on 'Add Staffer' Fill out staff info Click 'Next' Select uniform sizes Click 'Back' |  | 2025-04-11 | PASS | Previous menu shown with filled values | As expected
|  | M01_C03 |  | Check if uniform changes to correct uniform after going back and changing staff role | Click on 'Add Staffer' Fill out staff info Click 'Next' Select uniform sizes Click 'Back' Change staff role Click 'Next' |  | 2025-04-11 | PASS | Uniform menu shown with new uniform options | As expected
M02 | Remove staffer from system | M02_C01 |  | Check if staff can be removed from system | Click 'Retire Staffer' Select staff role Select staffer Click 'Retire' |  | 2025-04-11 | FAIL | Staffer removed from database | Crash selecting role, TypeError: 'NoneType' object is not subscriptable
M03 | Refresh orders table to show new staffers uniform | M03_C01 |  | Check if order tables updates with newly added and removed staff | Click 'Orders' tab Click 'Refresh' | Extra staff in system and previous scenarios ran | 2025-04-11 | PASS | Table showing a new staffer, and another removed | As expected
M04 | Place a uniform order | M04_C01 | R_05 | Check if order will be placed into system | Click 'Orders' tab Click 'Place Order' Select staff role Select staffer Click 'Next' Select atleast one uniform Click 'Finish' |  | 2025-04-11 | FAIL | Order placed | Crash selecting role, TypeError: 'NoneType' object is not subscriptable
|  | M04_C02 |  | Check if can go back to staff details with values present from uniform selection | Click 'Orders' tab Click 'Place Order' Select staff role Select staffer Click 'Next' Click 'Back' |  | 2025-04-11 | FAIL | Previous menu shown with filled values | Crash selecting role, TypeError: 'NoneType' object is not subscriptable
|  | M04_C03 |  | Check if uniform changes to correct uniform after going back and changing staff role | Click 'Orders' tab Click 'Place Order' Select staff role Select staffer Click 'Next' Click 'Back' Change selected role Click 'Next' |  | 2025-04-11 | FAIL | Uniform menu shown with new uniform options | Crash selecting role, TypeError: 'NoneType' object is not subscriptable
M05 | Reissue uniforms | M05_C01 |  | Check if selected uniforms will be reissued with a new order | Click 'Orders' tab Click 'Available Reissues' Select atleast one uniform Click 'Reissue Selected' | Valid reissues available in database | 2025-04-11 | FAIL | Reissue selected uniforms | Didn't display viable reissues
|  | M05_C02 |  | Check ability to reissue all orders | Click 'Orders' tab Click 'Available Reissues' Click 'Reissue All' | Valid reissues available in database | 2025-04-11 | FAIL | Reissue all uniforms | Didn't display viable reissues
M06 | View a report | M06_C01 |  | Check if reports can be viewed | Click 'Reports' tab Click 'View' on a report |  | 2025-04-11 | PASS | Display report as document in new window | As expected
M07 | Print a report | M07_C01 |  | Check if reports print | Click 'Reports' tab Click 'Print' on a report Select print to pdf option Click 'Print' View report from saved location |  | 2025-04-11 | PASS | Print document to PDF | As expected
|  | M07_C02 |  | Check if reports print from view option | Click 'Reports' tab Click 'View' on a report Click print button Select print to pdf option Click 'Print' View report from saved location |  | 2025-04-11 | PASS | Print document to PDF | As expected
M08 | Remove staffer from system | M08_C01 |  | Check if staff can be removed from system | Click 'Retire Staffer' Select staff role Select staffer Click 'Retire' |  | 2025-04-11 | PASS | Staffer removed from database | As expected
M09 | Place a uniform order | M09_C01 | R_05 | Check if order will be placed into system | Click 'Orders' tab Click 'Place Order' Select staff role Select staffer Click 'Next' Select atleast one uniform Click 'Finish' |  | 2025-04-11 | PASS | Order placed | As expected
|  | M09_C02 |  | Check if can go back to staff details with values present from uniform selection | Click 'Orders' tab Click 'Place Order' Select staff role Select staffer Click 'Next' Click 'Back' |  | 2025-04-11 | PASS | Previous menu shown with filled values | As expected
|  | M09_C03 |  | Check if uniform changes to correct uniform after going back and changing staff role | Click 'Orders' tab Click 'Place Order' Select staff role Select staffer Click 'Next' Click 'Back' Change selected role Click 'Next' |  | 2025-04-11 | PASS | Uniform menu shown with new uniform options | As expected
M10 | Reissue uniforms | M10_C01 |  | Check if selected uniforms will be reissued with a new order | Click 'Orders' tab Click 'Available Reissues' Select atleast one uniform Click 'Reissue Selected' | Valid reissues available in database | 2025-04-11 | PASS | Reissue selected uniforms | As expected
|  | M10_C02 |  | Check ability to reissue all orders | Click 'Orders' tab Click 'Available Reissues' Click 'Reissue All' | Valid reissues available in database | 2025-04-11 | PASS | Reissue all uniforms | As expected

## Integrity Testing
Scenario ID | Scenario Description | Case ID | Req. ID | Case Description | Steps/Query | Values | Pre-Conditions | Date | Status | Expected Results | Actual Results | Comments
I01 | Check validation of AddNewStaff procedure | I01_C01 |  | Fullname range check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'Mister James Robert Bullen of Watford, son of Mister Alistair Michael Bullen of Banham', sex = 'M', role = 1, hours = 40 |  | 2025-04-01 | PASS | Range error | As expected
|  | I01_C02 |  | Sex range check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'Male', role = 1, hours = 40 |  | 2025-04-01 | PASS | Range error | As expected
|  | I01_C03 |  | Role range check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = 100, hours = 40 |  | 2025-04-01 | PASS | Range error | As expected
|  | I01_C04 |  | Hours range check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = 1, hours = 400 |  | 2025-04-01 | PASS | No errors | As expected | Hours have no positive range limit due to being able to opt out of legal limit. Limiting to 40 hours will also create overtime edge case issue. May add later a high upper range check as anti-fraud messure
|  | I01_C05 |  | Negative role range check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = -1, hours = 40 |  | 2025-04-01 | PASS | Range error | As expected
|  | I01_C06 |  | Negative hours range check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = 1, hours = -1 |  | 2025-04-01 | FAIL | Range error | No errors | Shouldn't have negtive hours
|  | I01_C07 |  | Zero role range check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = 0, hours = 40 |  | 2025-04-01 | PASS | Range error | As expected
|  | I01_C08 |  | Zero hours range check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = 1, hours = 0 |  | 2025-04-01 | FAIL | No errors | Returns hours as 40 instead of 0
|  | I01_C09 |  | Fullname data type check | call AddNewStaff(fullname, sex, role, hours); | fullname = 10, sex = 'M', role = 1, hours = 40 |  | 2025-04-01 | FAIL | Data type error | Accepted number as a string | Technically not an issue, but better validation could prevent data entered in wrong field etc
|  | I01_C10 |  | Sex data type check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 10, role = 1, hours = 40 |  | 2025-04-01 | PASS | Data type error | As expected
|  | I01_C11 |  | Role data type check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = ten, hours = 40 |  | 2025-04-01 | PASS | Data type error | As expected
|  | I01_C12 |  | Hours data type check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = ten, hours = forty |  | 2025-04-01 | PASS | Data type error | As expected
|  | I01_C13 |  | Numerically correct but string for role | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = '1', hours = 40 |  | 2025-04-01 | FAIL | Data type error | Autoconverted string into numeric | Technically not an issue, may just ignore/not test for in future
|  | I01_C14 |  | Numerically correct but string for hours | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = 1, hours = '40' |  | 2025-04-01 | FAIL | Data type error | Autoconverted string into numeric | Technically not an issue, may just ignore/not test for in future
|  | I01_C15 |  | Fullname null check | call AddNewStaff(fullname, sex, role, hours); | fullname = null, sex = 'M', role = 1, hours = 40 |  | 2025-04-01 | PASS | Error, column can't be null | As expected
|  | I01_C16 |  | Sex null check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = null, role = 1, hours = 40 |  | 2025-04-01 | PASS | Error, column can't be null | As expected
|  | I01_C17 |  | Role null check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = null, hours = 40 |  | 2025-04-01 | PASS | Error, column can't be null | As expected
|  | I01_C18 |  | Hours null check | call AddNewStaff(fullname, sex, role, hours); | fullname = 'James Bullen', sex = 'M', role = 1, hours = null |  | 2025-04-01 | PASS | Error, column can't be null | As expected
I02 | Check validation of PurchaseUniform procedure | I02_C01 |  | Order range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 100, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 | Single valid staff entered into table | 2025-04-01 | PASS | Order created | As expected
|  | I02_C02 |  | Staff range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 100, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C03 |  | Item range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 100, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C04 |  | Colour range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 100, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C05 |  | Size range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XXXS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C06 |  | Quantity range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 100, bought = 0 |  | 2025-04-01 | PASS | Order created | As expected
|  | I02_C07 |  | Bought range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 100 |  | 2025-04-01 | FAIL | Range error | Order created
|  | I02_C08 |  | Negative order range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = -1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | FAIL | Range error | Order created
|  | I02_C09 |  | Negative staff range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = -1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C10 |  | Negative item range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = -1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C11 |  | Negative colour range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = -1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C12 |  | Negative quantity range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = -1, bought = 0 |  | 2025-04-01 | FAIL | Range error | Order created
|  | I02_C13 |  | Negative bought range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = -1 |  | 2025-04-01 | FAIL | Range error | Order created
|  | I02_C14 |  | Zero order range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 0, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Order created | As expected | Could make it so orders can't start from zero, only minor error to non-programmers looking at list fo orders
|  | I02_C15 |  | Zero staff range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 0, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C16 |  | Zero item range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 0, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C17 |  | Zero colour range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 0, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Range error | As expected
|  | I02_C18 |  | Zero quantity range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 0, bought = 0 |  | 2025-04-01 | PASS | Order created | As expected | Should prevent order of 0 items as does not make sense, but I've allowed so far
|  | I02_C19 |  | Zero bought range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Order created | As expected | 0 = False and it is a boolean
|  | I02_C20 |  | Order data type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 'one', staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Data type error | As expected
|  | I02_C21 |  | Staff data type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 'one', item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Data type error | As expected
|  | I02_C22 |  | Item data type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 'one', colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Data type error | As expected
|  | I02_C23 |  | Colour data type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 'one', size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Data type error | As expected
|  | I02_C24 |  | Size data type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 3, quantity = 3, bought = 0 |  | 2025-04-01 | FAIL | Data type error | Order created
|  | I02_C25 |  | Quantity data type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 'three', bought = 0 |  | 2025-04-01 | PASS | Data type error | As expected
|  | I02_C26 |  | Bought data type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 'zero' |  | 2025-04-01 | PASS | Data type error | As expected
|  | I02_C27 |  | Order null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = null, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Error, column can't be null | As expected
|  | I02_C28 |  | Staff null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = null, item = 1, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Error, column can't be null | As expected
|  | I02_C29 |  | Item null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = null, colour = 1, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Error, column can't be null | As expected
|  | I02_C30 |  | Colour null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = null, size = 'XS', quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Order created | As expected | Should I validate as only some items have no colour? Is it needed since only the allocation table can assign colour?
|  | I02_C31 |  | Size null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = null, quantity = 3, bought = 0 |  | 2025-04-01 | PASS | Error, column can't be null | As expected
|  | I02_C32 |  | Quantity null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = null, bought = 0 |  | 2025-04-01 | PASS | Error, column can't be null | As expected
|  | I02_C33 |  | Bought null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'XS', quantity = 3, bought = null |  | 2025-04-01 | PASS | Error, column can't be null | As expected
|  | I02_C34 |  | Size content check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought); | order = 1, staff = 1, item = 1, colour = 1, size = 'Hi', quantity = 3, bought = 0 |  | 2025-04-01 | FAIL | Invalid input error | No errors | Not sure if to validate here or in the front end
I03 | Check AddStaff validation | I03_C01 |  | Name range check | call AddStaff(fullname, sex, role, hours); | name = 'Mister James Robert Bullen of Watford, son of Mister Alistair Michael Bullen of Banham', sex = 'M', role = 1, hours = 40 |  | 2025-04-12 | PASS | Range error | As expected
|  | I03_C02 |  | Sex range check | call AddStaff(fullname, sex, role, hours); | name = 'James Bullen', sex = 'Male', role = 1, hours = 40 |  | 2025-04-12 | PASS | Range error | As expected
|  | I03_C03 |  | Role range check | call AddStaff(fullname, sex, role, hours); | name = 'James Bullen', sex = 'M', role = 100, hours = 40 |  | 2025-04-12 | PASS | Range error | As expected
|  | I03_C04 |  | Name type check | call AddStaff(fullname, sex, role, hours); | name = 1, sex = 'M', role = 1, hours = 40 |  | 2025-04-12 | FAIL | Data type error | As expected | Will validate for numbers in the front end
|  | I03_C05 |  | Sex type check | call AddStaff(fullname, sex, role, hours); | name = 'James Bullen', sex = 1, role = 1, hours = 40 |  | 2025-04-12 | FAIL | Data type error | As expected | Validated already by restricted inputs in front end. Why did I even write this test?
|  | I03_C06 |  | Role type check | call AddStaff(fullname, sex, role, hours); | name = 'James Bullen', sex = 'M', role = 'one', hours = 40 |  | 2025-04-12 | PASS | Data type error | As expected
|  | I03_C07 |  | Hours type check | call AddStaff(fullname, sex, role, hours); | name = 'James Bullen', sex = 'M', role = 1, hours = 'forty' |  | 2025-04-12 | PASS | Data type error | As expected
|  | I03_C08 |  | Name null check | call AddStaff(fullname, sex, role, hours); | name = null, sex = 'M', role = 1, hours = 40 |  | 2025-04-12 | PASS | Null error | As expected
|  | I03_C09 |  | Sex null check | call AddStaff(fullname, sex, role, hours); | name = 'James Bullen', sex = null, role = 1, hours = 40 |  | 2025-04-12 | PASS | Null error | As expected
|  | I03_C10 |  | Role null check | call AddStaff(fullname, sex, role, hours); | name = 'James Bullen', sex = 'M', role = null, hours = 40 |  | 2025-04-12 | PASS | Null error | As expected
|  | I03_C11 |  | Hours null check | call AddStaff(fullname, sex, role, hours); | name = 'James Bullen', sex = 'M', role = 1, hours = null |  | 2025-04-12 | PASS | Null error | As expected
I04 | Check RetireStaff validtion | I04_C01 |  | Range check | call RetireStaff(staff) | staff = 10 | No more than 9 staff in database | 2025-04-12 | FAIL | Range error | Calls | Doesn't have any negative effects, should it be considered a fail or checked?
|  | I04_C02 |  | Type check | call RetireStaff(staff) | staff = 'one' |  | 2025-04-12 | PASS | Data type error | As expected
|  | I04_C03 |  | Null check | call RetireStaff(staff) | staff = null |  | 2025-04-12 | FAIL | Null error | Calls | Same question as I04_C01
I05 | Check AllocatedUniform validation | I05_C01 |  | Sex range check | call AllocatedUniform(sex, role, hours) | sex = 'Male', role = 1, hours = 40 |  | 2025-04-12 | PASS | Range error | As expected
|  | I05_C02 |  | Role range check | call AllocatedUniform(sex, role, hours) | sex = 'M', role = 100, hours = 40 |  | 2025-04-12 | FAIL | Range error | Returns 0 rows | Not validated as it's treated as regular int rather than a primary ket
|  | I05_C03 |  | Role type check | call AllocatedUniform(sex, role, hours) | sex = 'M', role = 'one', hours = 40 |  | 2025-04-12 | PASS | Data type error | As expected
|  | I05_C04 |  | Hours type check | call AllocatedUniform(sex, role, hours) | sex = 'M', role = 1, hours = 'forty' |  | 2025-04-12 | PASS | Data type error | As expected
|  | I05_C05 |  | Sex null check | call AllocatedUniform(sex, role, hours) | sex = null, role = 1, hours = 40 |  | 2025-04-12 | FAIL | Null error | Returns rows | sex used in where check, where part of select statements care not for validation
|  | I05_C06 |  | Role null check | call AllocatedUniform(sex, role, hours) | sex = 'M', role = null, hours = 40 |  | 2025-04-12 | FAIL | Null error | Returns rows
|  | I05_C07 |  | Hours null check | call AllocatedUniform(sex, role, hours) | sex = 'M', role = 1, hours = null |  | 2025-04-12 | FAIL | Null error | Returns rows
I06 | Check FindStaff validation | I06_C01 |  | Range check | call FindStaff(role) | role = 100 |  | 2025-04-12 | FAIL | Range error | Returns no rows | Is it a fail if it returns nothing or failure of test case design?
|  | I06_C02 |  | Type check | call FindStaff(role) | role = 'one' |  | 2025-04-12 | PASS | Data type error | As expected
|  | I06_C03 |  | Null check | call FindStaff(role) | role = null |  | 2025-04-12 | FAIL | Null error | Returns no rows | Is it a fail if it returns nothing or failure of test case design?
I07 | Check PurchaseUniform validation | I07_C01 |  | Staff range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 10, item = 2, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 1 | No more than 9 staff in database | 2025-04-12 | PASS | Range error | As expected
|  | I07_C02 |  | Item range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 20, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Range error | As expected
|  | I07_C03 |  | Colour range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 100, size = 'XS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Range error | As expected
|  | I07_C04 |  | Size range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 'XXXS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Range error | As expected
|  | I07_C05 |  | Bought range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 'XS', quantity = 1, bought = 3, prevorder = 1 |  | 2025-04-12 | PASS | Range error | As expected
|  | I07_C06 |  | PrevOrder range check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 10 | No more than 9 orders in database | 2025-04-12 | PASS | Range error | As expected
|  | I07_C07 |  | Order type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 'one', staff = 1, item = 2, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Data type error | As expected
|  | I07_C08 |  | Staff type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 'one', item = 2, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Data type error | As expected
|  | I07_C09 |  | Item type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 'two', colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Data type error | As expected
|  | I07_C10 |  | Colour type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 'one', size = 'XS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Data type error | As expected
|  | I07_C11 |  | Size type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 1, quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Data type error | As expected
|  | I07_C12 |  | Quantity type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 'XS', quantity = 'one', bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Data type error | As expected
|  | I07_C13 |  | Bought type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 'XS', quantity = 1, bought = 'zero', prevorder = 1 |  | 2025-04-12 | PASS | Data type error | As expected
|  | I07_C14 |  | PrevOrder type check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 'one' |  | 2025-04-12 | PASS | Data type error | As expected
|  | I07_C15 |  | Order null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = null, staff = 1, item = 2, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Null error | As expected
|  | I07_C16 |  | Staff null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = null, item = 2, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Null error | As expected
|  | I07_C17 |  | Item null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = null, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Null error | As expected
|  | I07_C18 |  | Size null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = null, quantity = 1, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Null error | As expected
|  | I07_C19 |  | Quantity null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 'XS', quantity = null, bought = 0, prevorder = 1 |  | 2025-04-12 | PASS | Null error | As expected
|  | I07_C20 |  | Bought null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 'XS', quantity = 1, bought = null, prevorder = 1 |  | 2025-04-12 | PASS | Null error | As expected
|  | I07_C21 |  | PrevOrder null check | call PurchaseUniform(order, staff, item, colour, size, quantity, bought, prevorder); | order = 1, staff = 1, item = 2, colour = 1, size = 'XS', quantity = 1, bought = 0, prevorder = null |  | 2025-04-12 | PASS | Null error | As expected
I08 | Check StaffInfo validation | I08_C01 |  | Range check | call StaffInfo(row) | row = 10 | No more than 9 staff in database | 2025-04-12 | FAIL | Range error | Returns no rows | No validation with where condition
|  | I08_C02 |  | Type check | call StaffInfo(row) | row ='one' |  | 2025-04-12 | PASS | Data type error | As expected
|  | I08_C03 |  | Null check | call StaffInfo(row) | row = null |  | 2025-04-12 | FAIL | Null error | Returns no rows | No validation with where condition
I09 | Check OrderInfo validation | I09_C01 |  | Range check | call OrderInfo(row) | row = 10 | No more than 9 orders in database | 2025-04-12 | FAIL | Range error | Returns no rows | No validation with where condition
|  | I09_C02 |  | Type check | call OrderInfo(row) | row ='one' |  | 2025-04-12 | PASS | Data type error | As expected
|  | I09_C03 |  | Null check | call OrderInfo(row) | row = null |  | 2025-04-12 | FAIL | Null error | Returns no rows | No validation with where condition
I10 | Check 'Staff Details' menu validation | I10_C01 |  | Full name range check | Click on 'Add Staffer' Enter value Fill out rest of form Click 'Next' | 'Mister James Robert Bullen of Watford, son of Mister Alistair Michael Bullen of Banham' |  | 2025-04-12 | PASS | Does not allow | As expected
|  | I10_C02 |  | Hours range check | Click on 'Add Staffer' Enter value Fill out rest of form Click 'Next' | 1000 |  | 2025-04-12 | PASS | Does not allow | As expected
|  | I10_C03 |  | Full name type check | Click on 'Add Staffer' Enter value Fill out rest of form Click 'Next' | 123 |  | 2025-04-12 | PASS | Does not allow | As expected
|  | I10_C04 |  | Hours type check | Click on 'Add Staffer' Enter value Fill out rest of form Click 'Next' | 'text' |  | 2025-04-12 | PASS | Does not allow | As expected
|  | I10_C05 |  | Full name null check | Click on 'Add Staffer' Fill out rest of form Click 'Next' |  |  | 2025-04-12 | PASS | Validation warning box | As expected
|  | I10_C06 |  | Sex null check | Click on 'Add Staffer' Fill out rest of form Click 'Next' |  |  | 2025-04-12 | PASS | Validation warning box | As expected
|  | I10_C07 |  | Role null check | Click on 'Add Staffer' Fill out rest of form Click 'Next' |  |  | 2025-04-12 | PASS | Validation warning box | As expected
|  | I10_C08 |  | Hours null check | Click on 'Add Staffer' Fill out rest of form Click 'Next' |  |  | 2025-04-12 | PASS | Validation warning box | As expected
I11 | Check 'Staff Selection' menu validation | I11C01 |  | Role null check | Click 'Retire Staffer' Click 'Retire' |  |  | 2025-04-12 | PASS | Validation warning box | As expected
|  | I11C02 |  | Name null check | Click 'Retire Staffer' Select staff role Click 'Retire' |  |  | 2025-04-12 | PASS | Validation warning box | As expected
I12 | Check 'Uniform Selection' menu validation | I12_C01 | R_05 | Quantity range check | Click 'Orders' tab Click 'Place Order' Select staff role Select staffer Click 'Next' Select atleast one uniform Enter value Click 'Finish' | 1000 |  | 2025-04-12 | PASS | Does not allow | As expected
|  | I12_C02 | R_05 | Quantity type check | Click 'Orders' tab Click 'Place Order' Select staff role Select staffer Click 'Next' Select atleast one uniform Enter value Click 'Finish' | 'text' |  | 2025-04-12 | PASS | Does not allow | As expected
|  | I12_C03 | R_05 | Quantity null check | Click 'Orders' tab Click 'Place Order' Select staff role Select staffer Click 'Next' Select atleast one uniform Click 'Finish' |  |  | 2025-04-12 | PASS | Validation warning box | As expected

## Fetch Testing
Scenario ID | Scenario Description | Case ID | Req. ID | Case Description | Query | Date | Time | Comments
F01 | AddStaff() query speed | F01_C01 |  | 100 entry insert | call AddNewStaff('James Bullen', 'M', 1, 40); |  | 0.015
|  | F01_C02 |  | 200 entry insert | call AddNewStaff('James Bullen', 'M', 1, 40); |  | 0.031
|  | F01_C03 |  | 300 entry insert | call AddNewStaff('James Bullen', 'M', 1, 40); |  | 0.016
|  | F01_C04 |  | 400 entry insert | call AddNewStaff('James Bullen', 'M', 1, 40); |  | 0
|  | F01_C05 |  | 500 entry insert | call AddNewStaff('James Bullen', 'M', 1, 40); |  | 0.016
F02 | RetireStaff() query speed | F02_C01 |  | 100 entry delete | call RetireStaff(100); |  | 0.016
|  | F02_C02 |  | 200 entry delete | call RetireStaff(rand()*(100-1)+1); |  | 0.031
|  | F02_C03 |  | 300 entry delete | call RetireStaff(rand()*(100-1)+1); |  | 0.016
|  | F02_C04 |  | 400 entry delete | call RetireStaff(rand()*(100-1)+1); |  | 0.031
|  | F02_C05 |  | 500 entry delete | call RetireStaff(rand()*(100-1)+1); |  | 0.015
F03 | AllocaredUniform()query speed | F03_C01 |  | SELECT query | call AllocatedUniform('M', 1, 40); |  | 0.00045375
F04 | NextOrderNumber() query speed | F04_C01 |  | 100 entry select | call NextOrderNumber(); |  | 0
|  | F04_C02 |  | 200 entry select | call NextOrderNumber(); |  | 0
|  | F04_C03 |  | 300 entry select | call NextOrderNumber(); |  | 0
|  | F04_C04 |  | 400 entry select | call NextOrderNumber(); |  | 0
|  | F04_C05 |  | 500 entry select | call NextOrderNumber(); |  | 0
F05 | FindStaff() query speed | F05_C01 |  | 100 entry select | call FindStaff(rand()*(7-1)+1); |  | 0
|  | F05_C02 |  | 200 entry select | call FindStaff(rand()*(7-1)+1); |  | 0
|  | F05_C03 |  | 300 entry select | call FindStaff(rand()*(7-1)+1); |  | 0
|  | F05_C04 |  | 400 entry select | call FindStaff(rand()*(7-1)+1); |  | 0
|  | F05_C05 |  | 500 entry select | call FindStaff(rand()*(7-1)+1); |  | 0
F06 | PurchaseUniform() query speed | F06_C01 |  | 100 entry insert | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, 0); |  | 0
|  | F06_C02 |  | 200 entry insert | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, 0); |  | 0.032
|  | F06_C03 |  | 300 entry insert | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, 0); |  | 0.016
|  | F06_C04 |  | 400 entry insert | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, 0); |  | 0
|  | F06_C05 |  | 500 entry insert | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, 0); |  | 0.016
|  | F06_C06 |  | 100 entry insert and update | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, rand()*(100-1)+1); |  | 0.015
|  | F06_C07 |  | 200 entry insert and update | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, rand()*(100-1)+1); |  | 0.016
|  | F06_C08 |  | 300 entry insert and update | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, rand()*(100-1)+1); |  | 0.032
|  | F06_C09 |  | 400 entry insert and update | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, rand()*(100-1)+1); |  | 0.016
|  | F06_C10 |  | 500 entry insert and update | call PurchaseUniform(1, 1, 2, 1, 'XS', 3, 0, rand()*(100-1)+1); |  | 0.031
F07 | AvailableReissues() query speed | F07_C01 |  | 100 entry select | call AvailableReissues(); |  | 0
|  | F07_C02 |  | 200 entry select | call AvailableReissues(); |  | 0
|  | F07_C03 |  | 300 entry select | call AvailableReissues(); |  | 0.015
|  | F07_C04 |  | 400 entry select | call AvailableReissues(); |  | 0
|  | F07_C05 |  | 500 entry select | call AvailableReissues(); |  | 0
F08 | StaffInfo() query speed | F08_C01 |  | 100 entry select | call StaffInfo(1); |  | 0
|  | F08_C02 |  | 200 entry select | call StaffInfo(1); |  | 0
|  | F08_C03 |  | 300 entry select | call StaffInfo(1); |  | 0.016
|  | F08_C04 |  | 400 entry select | call StaffInfo(1); |  | 0.015
|  | F08_C05 |  | 500 entry select | call StaffInfo(1); |  | 0
F09 | OrderInfo() query speed | F09_C01 |  | 100 entry select | call OrderInfo(1); |  | 0
|  | F09_C02 |  | 200 entry select | call OrderInfo(1); |  | 0
|  | F09_C03 |  | 300 entry select | call OrderInfo(1); |  | 0.016
|  | F09_C04 |  | 400 entry select | call OrderInfo(1); |  | 0
|  | F09_C05 |  | 500 entry select | call OrderInfo(1); |  | 0
F10 | MostOrdered() query speed | F10_C01 |  | 100 entry select | call MostOrdered(); |  | 0
|  | F10_C02 |  | 200 entry select | call MostOrdered(); |  | 0
|  | F10_C03 |  | 300 entry select | call MostOrdered(); |  | 0
|  | F10_C04 |  | 400 entry select | call MostOrdered(); |  | 0.016
|  | F10_C05 |  | 500 entry select | call MostOrdered(); |  | 0
F11 | StaffStatistics() query speed | F11_C01 |  | 100 entry select | call StaffStatistics(); |  | 0
|  | F11_C02 |  | 200 entry select | call StaffStatistics(); |  | 0
|  | F11_C03 |  | 300 entry select | call StaffStatistics(); |  | 0
|  | F11_C04 |  | 400 entry select | call StaffStatistics(); |  | 0
|  | F11_C05 |  | 500 entry select | call StaffStatistics(); |  | 0
F12 | AllocationTable() query speed | F12_C01 |  | SELECT query | call AllocationTable(); |  | 0.016
F13 | SupplierInfo() query speed | F13_C01 |  | SELECT query | call SupplierInfo(); |  | 0